DRAFT

NPLCC Project Management and Accountability Practices

Table of Contents

(To be added)

Introduction

The North Pacific Landscape Conservation Cooperative (NPLCC) provides data and information to support sustainable natural resource management in the face of climate change (http://www.northpacificlcc.org/) NPLCC projects implemented to achieve this purpose are funded with Federal appropriations administered through the U.S. Fish and Wildlife Service (FWS) as the hosting organization and are frequently augmented (or even principally funded or cost-shared) by a diverse variety of State, Tribal, Federal, First Nation, Provincial, and NGO organizations.  The essence of NPLCC projects is collaborative—in development, purpose, and support.

This document will serve as guidance for the development, implementation, and management of each NPLCC-sponsored project from initiation to close-out.  In awarding and managing project related funding, foremost objectives of the NPLCC are accountability for use of funds and the relevance of project outcomes and products to improved conservation and sustainable natural resource management.  The guidance, or its relevant elements, will also be applicable for some work undertaken by NPLCC partners not receiving NPLCC support, as a general tool for cooperatively managing data and information provided to the NPLCC to improve the response to shared natural resource challenges. This guidance will help assure that NPLCC projects:

- meet  Federal and other applicable requirements for contracting and financial management;

- are free from any conflicts of interest or appearances of conflict of interest among both NPLCC members and project partners;

- fulfill all reporting requirements, relevant data and information documentation, and delivery standards in a timely manner;

- contribute to a common pool of readily available, practitioner-relevant knowledge supporting natural resource management in the face of climate challenges throughout the NPLCC eco-region;

- facilitate communication and collaboration in developing effective, on-the-ground approaches to climate challenges.

This document is organized around three sequential activities associated with developing, awarding, implementing, and completing a given project, beginning with high level strategic planning and ending with project data and information management and communication to inform those who most need the information.  Figure 1 illustrates the flow of these main activities and provides a guide to the structure of this document.

Figure 1.  Project Management and Accountability Steps

Section 1.  Identification of Project Priorities

The NPLCC has adopted a tiered planning approach that accounts for resource and climate change issues encompassing all the program’s partners, throughout the full geography of the eco-region. Once the NPLCC partnership was initially established, priorities were set at the highest level, with identification of big-picture issues and the definition of goals and objectives for the Partnership (link to the NPLCC Charter).  Within this context, planning was then stepped down to more tractable, detailed elements ultimately leading to project development and implementation.  How this NPLCC planning process will be used in project management is summarized below.

NPLCC S-TEK Strategy.  At the highest level, NPLCC priorities will be identified in the NPLCC Strategy for Science and Traditional Ecological Knowledge (hereafter, “the Strategy”, and available here) and will be consistent with the National LCC purpose (http://lccnetwork.org/).The Strategy will be revised periodically by the Science and Traditional Ecological Knowledge Subcommittee (S-TEK Subcommittee), on a schedule determined by the Steering Committee, which oversees all aspects of the NPLCC. The purpose of the Strategy is to provide overall direction and guidance for activities related to landscape-level conservation and sustainable resource management in the face of climate change within the NPLCC eco-regional area.

During development of the Strategy, it was essential to narrow the focus of the numerous challenges associated with climate change impacts on valued natural and cultural resources, to a smaller number of topics.  These topics needed to be most relevant to resource practitioners on the ground and fill critical gaps not likely to be addressed by individual partners working alone Version 1.0 of the Strategy completed in November 2012 for the 2013-2016 planning period identified five Priority Topics for NPLCC strategic planning purposes.  All NPLCC projects will be guided by these or subsequent Priority Topics and will further comply with Guiding Principles identified in the Strategy.

NPLCC Implementation Plan.  More detailed guidance for project development will be provided by the Implementation Plan for NPLCC Science and Traditional Ecological Knowledge (Implementation Plan, available here).  As with the Strategy, this Implementation Plan will be developed by the S-TEK Subcommittee and approved by the Steering Committee.  Revision of the Implementation Plan will occur annually. The Implementation Plan further steps down the broad guidance of the Strategy to a set of Priority Activities corresponding to the Priority Topics in the Strategy. The Priority Activities will be specific enough to guide annual development of NPLCC projects, but broad enough to allow for creativity and innovation by the Principal Investigators (PIs) who carry out the projects.

Section 2.  Solicitation and Award of Projects

On an annual planning cycle, projects may be selected through a competitive process via a Request for Proposals (RFP), a process widely used in research funding.  Alternatively, projects may be directed non-competitively to an appropriate organization or investigator chosen as the best for a particular issue.  Competed projects have the advantage of stimulating innovation and forward-looking approaches to climate change adaptation, through the competing proposals submitted by subject matter experts. Directed projects may be appropriate when an organization is uniquely qualified; when a qualified organization volunteers most or all of the funding for, or offers to host a particular line of work beyond the project period; or when other cost-savings occur.  Award of documents, directed or competed, will meet federal guidelines.

To determine the portfolio mix of competed and directed projects for a given annual funding cycle, the NPLCC Science Coordinator will consult with the S-TEK Subcommittee Chair to develop a recommendation for presentation to the S-TEK Subcommittee.  The S-TEK Subcommittee will then deliberate on the merits of the recommendation in view of the currently identified Priority Activities in the Implementation Plan relative to the ongoing activities of partner organizations.  Recommendations from the S-TEK Subcommittee for any directed funding will be provided to the Steering Committee for deliberation and approval.

Specific Project Eligibility. In some cases, restrictions may be made on who is eligible to receive project funding.  Projects related to TEK may fall into this category.  The NPLCC emphasizes the role of TEK of Tribes and First Nations in shaping human response to climate change influences on natural and cultural resources. Tribes and First nations have proprietary rights to their TEK and it is for them to decide if they want to share that knowledge and if so, what TEK to share and how and with whom to share it. TEK does not fall within the same provenance as scientific findings that are freely and publically shared. Mixtures of knowledge derived from both TEK and research may be the basis for Tribal and First Nation natural resource management in significant NPLCC environments.  For these reasons, TEK-related projects may be awarded to a particular Tribe or First Nation.

Directed and Competed Projects

Directed Projects.  Some circumstances may call for non-competed project awards to particular organization(s), without the use of an RFP and without review of multiple competing proposals. For example, a sustained commitment by a particular organization to ongoing work, such as data management, could best serve the NPLCC mission through a non-competed initial project award. A qualified NPLCC partner organization may contribute most or all of the funding for a given project within the mission of both the NPLCC and the contributing organization, and therefore be the best qualified entity for the work. All awards of project funding for projects managed by the FWS will meet Department of Interior regulations and other partners will meet their requirements.

Review of Directed Projects:  Following a staff recommendation and agreement by the S-TEK Subcommittee and Steering Committee on any identified directed project, the NPLCC Science Coordinator will request a full proposal from the identified project PI.  Review will then follow the NPLCC process for full proposal review (above).

Competed Projects. Competed projects will be selected from among proposals submitted in response to a publically announced RFP.  It is anticipated that the NPLCC will typically receive far more proposals than can be funded.  The S-TEK Subcommittee may recommend that an initial request for pre-proposals be used to narrow the field of potential projects.  Calling for pre-proposals has the advantage of highlighting similar proposed projects early in planning, sometimes authored by PIs who are unaware of each other’s proposed work.  This situation offers the opportunity for collaboration to occur during full proposal development. Because development of full proposals involves a substantial time and work load for PIs and reviewers alike, the use of pre-proposals may be more efficient in focusing NPLCC efforts on a smaller number of qualified projects with potentially greater collaboration.

The NPLCC will utilize one of two approaches: (1) RFP calls for full proposals which are reviewed by the NPLCC for award; or (2) RFP calls for shorter pre-proposals, reviewed by the NPLCC followed by review of a smaller number of invited full proposals for award. Elements of the award process for competed projects are shown in Figure 2, and are detailed below.

Figure 2.  Proposal and pre-proposal Review Process

Request for Proposals: A RFP will be drafted by the NPLCC Science Coordinator and reviewed by the S-TEK Chair and any volunteering S-TEK members.  The RFP will cite applicable NPLCC guidance documents (Strategy, Implementation Plan, this document, and other guidance as appropriate).  The RFP will include:

- a clear description of the funding opportunity, eligibility and application requirements, the  Priority Activities being addressed, and a link to the Implementation Plan that has led to the RFP;

- submission instructions, application review information and award administration

- a recommended template, or link to an on-line entry system, corresponding to pre-proposal (Appendix I: Pre-proposal template example) or proposal (Appendix II: Proposal template example) submission as previously determined by the S-TEK;

- project requirements, including:

  - schedule and progress reporting requirements;

  - requirement for development of a Data Management Plan (DMP);

  - final deliverables requirements;

  - communication expectations for project outcomes;

  - a project budget;

  - PI and project participant credentials guidance

The RFP will be published on Grants.gov and posted on the NPLCC website, an announcement will be sent to NPLCC contacts, and NPLCC members will publicize the RFP as widely as possible within their respective organizations.

Review of Pre-proposals: If the RFP requests project pre-proposals, the primary intent of the review is to determine the appropriateness of the proposed projects. Criteria for clarity and responsiveness, partner engagement, and significance of the work to conservation and sustainable natural resource management in a climate change context will be used to score the pre-proposals.  Pre-proposal review is largely a strategic assessment of proposed work as compared to NPLCC goals and information needs, and will therefore be undertaken by NPLCC S-TEK members and appropriate designees.  Pre-proposal review scores will be used to select a smaller set of potential projects to prepare and submit full proposals for more detailed review. For pre-proposals, the following activities will be completed:

- Pre-proposals screened for compliance with RFP guidance (Science Coordinator).

- Basic meta data compiled concerning pre-proposals received, for use during project evaluation (Science Coordinator).

- Conflict of Interest and Confidentiality Statement agreed to in writing (Appendix III: Conflict of interest and confidentiality statement) (All Reviewers).

- Pre-proposal review scores for each pre-proposal completed by a minimum of (3) reviewers for all criteria included in the RFP for pre-proposals (with a focus on management application); reviews conducted in strict confidentiality (S-TEK Subcommittee members and designees).

- Joint reviewer deliberation (by meeting or conference call) on project rankings based on review scores and general discussion on the merits of proposed projects (Science Coordinator and reviewers only).

- Identification of similarities among pre-proposals, and consideration on whether to invite one or more  joint collaborative full proposal(s), dependent on PIs being willing to share information and collaborate (Science Coordinator, with S-TEK Subcommittee member input).

- Invitation and guidance provided to selected PIs to submit full proposals, corresponding to agreed-upon pre-proposal review results, and including any decision(s) to invite joint proposals (Science Coordinator).

Review of Full Proposals: Full proposal review, regardless of whether pre-proposals have been previously requested and reviewed, will be more substantive, and often more technical due to the higher level of detail requested of a full proposal.  Scientific or technical proposals will need to include, but not be limited to, elements such as experimental design, methods, data acquisition and management, a detailed budget, and PI credentials. Full proposal reviewers may be selected primarily for scientific or technical expertise as peers, and the proposal review template will include additional criteria included in the RFP.

Full proposal review teams may be expanded to include qualified peer reviewers, as long as there is no conflict of interest. Review of full proposals will follow the same steps as for pre-proposals review (above), however reviewers evaluate the additional criteria identified in the RFP for full proposals. Should review findings reveal the need to modify the proposal for a given project, the Science Coordinator will discuss review findings with the Project PI, and will negotiate any revisions to the proposal prior to project implementation.

Project Selection and Award

S-TEK Subcommittee Project Award Recommendations to Steering Committee.  Following review of project pre-proposals and proposals, the S-TEK Subcommittee will make recommendations to the Steering Committee concerning full proposals to invite (if applicable) and recommended projects to award.  They will identify a list of projects that are justified by positive proposal review findings concerning proposal merit.  The S-TEK Subcommittee Chair will present project award recommendations to the Steering Committee prior to award of new projects. By prior agreement, the Steering Committee may delegate deliberation on these S-TEK Subcommittee recommendations to an Ad Hoc Committee comprised of the Steering Committee Co-Chairs and the S-TEK Subcommittee who in this case will meet with the NPLCC Coordinator and Science Coordinator. In the event of such a delegation, other members of the Steering Committee will be invited to participate in the deliberation at their option.

The S-TEK Subcommittee Chair and Science Coordinator will summarize the results of S-TEK Subcommittee project review for the Steering Committee or its agreed-upon representatives including:

- Metadata concerning pre-proposals and proposals received by the NPLCC for consideration;

- Review process carried out and findings such as project rankings;

- Deliberation on the mix of competed and directed projects;

- Deliberation on project portfolio balance;

- Recommendation to the Steering Committee for a suite of projects to award for the current planning cycle.

Project Portfolio Balance. Prior to the invitation of full proposals or the award of projects, the Steering Committee may consider review findings in light of the overall NPLCC project portfolio.  In considering implementation of particular projects, the Steering Committee may consider issues not determined solely by project review scores, such as mission balance among the diverse geographic environments within the NPLCC, the balance of natural science, social science, TEK or other approaches, and the relative participation of partners (Tribes, First Nations, US States, and Province of British Columbia).  Both in development of the RFP, and in review of proposals, the Steering Committee may seek projects focused primarily on one or a few Priority Activities in a planning cycle, or may seek to implement projects across multiple Priority Activities in the same planning cycle.

Awards.  In no case will the Steering Committee choose to award a project not justified by the merits of its proposal as determined by review findings. Following a decision by the Steering Committee or delegated concerning the award of projects, the NPLCC Science Coordinator will contact the successful PIs, and subsequently public announcement of the awards will be issued and posted to the NPLCC website.

As the official Federal hosting agency of the NPLCC, the FWS will implement all necessary contracts and cooperative agreements to award projects selected by the NPLCC Steering Committee for funding provided by FWS or provided by partners to support NPLCC projects where those partners desire FWS administration of contracting.  All required Department of Interior and FWS contracting requirements will be followed.  If another agency or organization provides funds directly to another entity for a NPLCC selected project, their contracting and funding requirements will be followed.

Section 3.  Project Implementation

Tracking and Review

Project Management Database. Each project implemented by the NPLCC will be entered into the program’s Project Management Database (Appendix IV: "Master" project table (under development)). The intent of this database is to list in a single location all the information necessary to track and manage each project. The database will include the project title, funding amount and duration, Lead PI, other cooperating investigators, reporting deliverable due dates, and other pertinent information.  The Database will be available to all NPLCC members and staff, and will facilitate progress reporting by the Science Coordinator to the S-TEK Subcommittee.

Project Tracking.  Following each project award, the project PI will report progress to the NPLCC Science Coordinator on at least an annual basis.  PIs will utilize the NPLCC progress reporting template (Appendix V: Project progress report template example (under development)) for all progress reports.  Mid-year progress report will be required for all one-year projects.  Semi-annual or annual progress reports will be required each year during the project period for multi-year projects. The NPLCC Science Coordinator will review the progress of all active projects, including the dates upon which deliverables or other requirements are due, and when these required deliverables are actually received. The NPLCC Science Coordinator will assure that all progress reports are posted to the NPLCC web site, and will report on the progress of all active projects to the S-TEK Subcommittee during regular meetings. The Science Coordinator will report on any concerns, issues, or needs for additional project guidance or communication arising during progress tracking, and on an as-needed basis, progress will be reported to the Steering Committee.

Project Review.  The NPLCC seeks project outcomes that provide data and/or information relevant to sustainable natural resource management in a changing climate within the NPLCC eco-region. Project outcomes will range from numerical physical and biological measurements with derived statistics and interpretations, to digital geographic data layers, models, and ethnographic survey responses involving societal belief systems.   Project deliverables will therefore vary to include technical reports and data sets (e.g. hydrologic temperature regimes) to policy “white papers” (e.g. use of TEK in climate change adaptation).

To assure that the data and information objectives of the NPLCC are achieved, Data Management Plans (DMPs) will be required for each project. The data management practices of the NPLCC are intended to be generally consistent with requirements of the National LCC Network, National Climate Change and Wildlife Science Center, the overlapping  Climate Science Centers, and the National Science Foundation.

If deemed appropriate by the Science Coordinator, a review team will be convened to meet with the PI and others on their team to discuss project methods, draft results, or other intermediate activities to ensure the project is on track and final products will meet the goals and objectives of the projects.  This will be arranged at a time convenient for the PIs and when there are outcomes to discuss.  Discussions on possible outreach to managers and other product end users may be included.

In keeping with the diversity of NPLCC project outcomes and deliverables, the term “data” will be used broadly to include “textual information, numeric information, instrumental readouts, equations, statistics, images (whether fixed or moving), diagrams, and audio recordings. It includes raw data, processed data, derived data, published data, physical samples, and archived data. It includes the data generated by experiments, by models and simulations, and by observations of natural phenomena at specific times and locations. It includes data gathered specifically for research as well as information gathered for other purposes that is then used in research. This definition of data also includes any custom code or applications that were developed to aid in data analysis or transformation and are necessary to understand the data. Code and applications must include adequate documentation and/or within code comments to understand the function.” (LCC Data Management Best Practices Part 1, 2013)

Data Management Plan. For each NPLCC project, the PI will submit a DMP to the Science Coordinator within 90 days of the project award (Appendix VI:  DMP template).  The NPLCC DMP is consistent with the Climate Science Center’s DMP to facilitate use with jointly funded projects.  The DMP will reflect an overall consideration of the project including the information needs that the project is designed to fulfill, project design, methodology, computation and analysis, data storage and archiving, and product delivery. The DMP will guide implementation of standard data documentation practices throughout the project life.  The project budget will realistically reflect the proportion of project resources needed to assure appropriate data management activities are accomplished under the DMP as part of the project.  Data delivery will ensure that all data and information generated by the project is easy to find and access and includes sufficient documentation for use in ongoing post-project NPLCC data management and natural resource application (however, see exceptions concerning limitations on the public disclosure of some kinds of data, under Delivery of Project Outcomes, below). NPLCC guidance will differ for technical and non-technical NPLCC projects as defined and summarized below.  Assistance will be provided by the NPLCC data management specialist if requested.  The NPLCC will work with Tribes and First Nations on the use of the DMP since they will not be required to enter data or information related to proprietary or sensitive TEK. Tribes and First Nations will be given the latitude to enter what they chose to share.

Technical Projects:  Technical projects are those projects that acquire technical or scientific data and provide information to the NPLCC beyond “textual information.” Many NPLCC projects will be technical, for example applying a formal methodology, collecting field data or compiling and analyzing previously published data, providing numerical or interpretive analyses, modeling, geo-referencing specific data, and drafting a report.

Submittal of the DMP will consist of completion of entries into the NPLCC on-line DMP template provided as part of the Science Base/LC-Map systems or provided via the NPLCC website.  Technical project DMPs will:

- Address all critical aspects of the data management and use: plan, collect, assure, describe, preserve, discover, integrate, and analyze;

- Document data acquired from existing data sources (origin, documentation, and use restrictions);

- Anticipate the full array of data products generated using NPLCC funds including primary (i.e. field-collected) and secondary (i.e. derived from analysis or modeling) sources;

- Describe how new data will be collected and how existing data will be leveraged or re-purposed, including any relevant analytical tools and software;

- Articulate quality assurance/quality control procedures;

- Define the means to achieve appropriate metadata standard for all datasets;

- Identify anticipated data formats;

- Describe a plan for long-term storage of samples and physical collections (if appropriate);

- Specify how and when the data will be transferred to LCC custody;

- If applicable, describe archiving, data delivery, and long-term maintenance measures.

Non-Technical Projects:  Projects will be considered non-technical if the deliverable is a “white paper,” a narrative report without quantitative data, development of policy recommendations, or some ethnographic or other findings in the form of a report that is primarily narrative. However, most projects will have some elements of information collection even if they do not involve quantitative data and a science design. These projects will need at least some of the elements of a DMP.  For predominantly non-technical projects, the NPLCC Science Coordinator will work with the project PI to determine which elements of the DMP Template apply, and the project PI will then provide responses to those elements, on the same schedule that a technical project provides a full DMP.

Deliverables Review. In the public trust, the NPLCC seeks to ensure high quality and maximum utility of data and information products resulting from NPLCC-funded projects. All draft project deliverables will undergo review to help meet this goal.  The Science Coordinator will determine whether or not the draft deliverables should undergo peer review and will work with the PIs.  As noted above, delivery of TEK information and data is not required and Tribes and First Nations will only share what they determine to be appropriate to share.  Prior to the start of the project, the Science Coordinator and PIs from Tribes and First Nations will identify appropriate deliverables.

Peer review “is a form of deliberation involving an exchange of judgments about the appropriateness of methods and the strength of the author’s inferences. Peer review involves the review of a draft product for quality by specialists in the field who were not involved in producing the draft. ” While the term “peer review” is often associated with scientific reviews, this definition is general enough to apply to essentially all NPLCC project deliverables.

The purpose of peer review will be to improve draft deliverables through appropriate revisions prior to being delivered as final products to the NPLCC. Based on the results of peer review, the NPLCC Science Coordinator will communicate with the PI to address review comments and agree upon the nature of any revisions needed during development of the final deliverables. Adequate time will be included in all contracts and agreements to allow time for peer review if needed.  The following steps will be undertaken for review of draft final deliverables, under the general oversight of the Science Coordinator:

Compliance Review:  All deliverables will be initially screened for completeness and for fulfillment of contract and agreement requirements.  The compliance review will be carried out by the Science Coordinator, and any shortfalls will be communicated to the project PI, so that a complete deliverable is provided for substantive peer review.

Identification of Peer Reviewers:  For scientific and technical deliverables deemed appropriate to have peer review, reviewers will be sought who have education and/or experience sufficient to comment on the work of others in a particular field of expertise. In a more general sense, reviewers of non-technical deliverables must be similarly qualified.  If a scientific and technical deliverable will be undergoing peer review through a professional publication, the NPLCC will accept that review to fulfill this step.  Review steps and their corresponding responsibilities are:

- Call for nomination of peer reviewers sent to NPLCC members and the lead PI of the project (Science Coordinator):

- S-TEK members may be personally qualified to participate as a reviewer and may volunteer themselves, and are also encouraged to nominate qualified, willing reviewers based on professional networks.

- PIs are in a position to know colleagues in their field who meet reviewer qualifications, and may nominate individuals as potential reviewers.

- The Science Coordinator is not bound by any particular NPLCC member or PI nomination, but may use discretion to draw from the overall pool of nominees to identify the most objective, qualified reviewers.

- At least (3) reviewers will be designated for anonymous, confidential review of each project draft deliverable (Science Coordinator in consultation with S-TEK Subcommittee members):

- The anonymity provision recognizes that peer reviewers will carry out objective, merit-based reviews free from complications resulting from professional or personal links to authors.

- The confidentiality provision assures that the draft deliverable is distributed solely for review purposes, and is deliberative and pre-decisional only, and so will not be disclosed or released by reviewers.

- Reviewers asked to acknowledge in writing their compliance with the NPLCC conflict of interest policy (Science Coordinator).

- Reviewers provided with review guidance and template (Science Coordinator).

Peer Review:

- Reviewers will be asked to complete their reviews within 21 days of receiving the deliverable.  They will be provided with a review template (Appendix VII: Deliverable peer review template (under development)) (Science Coordinator).

- Reviewers transmit findings to Science Coordinator (Reviewers).

Reconciliation of Reviewer Comments:

- Reviews provided anonymously and in their entirety to project PI unless reviewers note the comments are for the Science Coordinator only (Science Coordinator, who serves as the referee for peer review).

- After receipt of the reviews, reconciliation will be developed within 21 days or another agreed upon time, based on peer review recommendations (PI working with author team):

- Reconciliation is a point-by-point written author response to review comments and recommendations.  Typically, this process results in specific deliverable revisions, and for comments not leading to revisions, PI provides a written refutation of review suggestion(s) with reasons provided as to why review recommendations were not incorporated.

- Reconciliation and revised deliverable assessed against review comments for adequacy (Science Coordinator):

- If a review issue cannot be resolved by the Science Coordinator working with the project PI and author team, advice to identify a path toward resolution will be sought from the NPLCC Coordinator and the Chairs of the S-TEK Subcommittee and Steering Committee.

Delivery of Project Outcomes

Unless agreed to otherwise in a specific contract or agreement, PIs will submit to the NPLCC a digital copy of any final report(s), as approved following peer review and reconciliation.  PIs will further provide the NPLCC with all raw data, derived data products, and other supporting materials created or gathered in the course of work under NPLCC-supported research, following their project-specific DMPs.

Report Delivery.  All NPLCC projects will generate a final written report with summaries of all phases of the project work and a description of end products within 90 days after conclusion of the project.  Some of the project final reports will generate a final written report in the form of a manuscript with additional detail. Once peer review is complete and the report is approved by the NPLCC Science Coordinator or NPLCC Coordinator, the deliverable will be posted on the NPLCC website. The report will also be used in NPLCC communications aimed at getting program findings into the hands of natural resource practitioners who face challenges related to climate change. Proposal, contract, or agreement provisions will frequently include verbal reporting in the form of presentation(s) by the PI or project team, to communicate project outcomes.  Reporting may be in person in the form of presentations at various venues, or by audio/video streaming; their principal focus may be on information transfer to natural resource practitioners.

Data Delivery.  While the function of a final project report is to summarize findings and interpretations of those findings, the full range of data and information gathered or produced by the project is not typically included in the report in a complete or useable form.  For example, raw or derived digital geographic data layers require different delivery than a report or manuscript can provide.  Raw data, including all elements included in the data definition, will be provided in the proper format(s) for delivery to the NPLCC for ongoing use in data and information server and analysis systems.

Delivery Responsibility: The project PI will preserve and transfer all data and data products to the NPLCC in commonly accepted formats needed for long term applications. These standards do not supersede the legal requirements imposed upon organizations to restrict public access to data; however such restrictions must be addressed in advance in the project proposal and DMP.

- PIs will be responsible for delivering a copy of all data, appropriate metadata, and other supporting information to the NPLCC Science Coordinator. Unless agreed to otherwise, the PI or designee will enter raw data into Science Base or another NPLCC selected storage system:

- The NPLCC will provide appropriate access to data systems. The purpose of the NPLCC raw data archive is to provide protection against data loss;

- Raw data is not intended to be accessible by other researchers or the public;

- Upon transfer of raw data from PIs, NPLCC becomes responsible for long-term maintenance and potential eventual public access to this data.

- PIs will be responsible for the quality, completeness, and description of project data, metadata and associated products delivered to the NPLCC.

Delivery Schedule:  Unless otherwise agreed to, all data and derived data products will be submitted to NPLCC no later than 90 days after the conclusion of the project.

Metadata: Metadata will be provided for all project data sets and products. A complete metadata record will be submitted by the PI to the Science Coordinator for the project as a whole (Project Metadata) and for each individual data product delivered (Dataset Metadata). If required, the PI will provide metadata through data entry into digital systems.

- Content and format will follow recognized metadata protocol, such as the Federal Geospatial Data Committee Content Standard for Digital Geospatial Metadata (FGDC CSDGM) or International Standards Office (ISO) 19115/19119 protocols.

- If a project re-purposes or leverages an existing data set, metadata will cite the source data reference and link to the data.

- Some sources for metadata creation and support include: FGDC Geospatial Metadata Tools: http://www. fgdc. gov/metadata/geospatial-metadata-tools/LC MAP Metadata Tool: https://www. sciencebase. gov/catalog/?community=LCMAP and USGS Online Metadata Editor: http://mercury. ornl. gov/OME/ EPA Metadata Editor:https://edg. epa. gov/EME/mp Metadata Parser: http://geology. usgs. gov/tools/metadata/tools/doc/mp. Html

Proprietary Data and Software:  PIs who will use or create proprietary data affecting terms of information release or types of data use by the NPLCC will document proprietary elements in the proposal and DMP. TEK Data from Tribes and First Nations is recognized as being proprietary.

- Documentation will clearly state what information, data, and conclusions cannot be released to the public upon conclusion of the project. All data deemed sensitive, privileged, or subject to restricted access will be identified and appropriately labeled by the PI upon submission to NPLCC.

- Policies for access to these data will be negotiated between the PIs and the NPLCC Science Coordinator, or Coordinator as necessary, and documented in writing, prior to project implementation. Legal requirements restricting information and data access will be clearly stated in the project proposal and DMP.

Physical Specimens:  PIs will deposit any samples, genetic material, and/or physical collections associated with their research in a recognized and approved repository or collection within their discipline, and will provide the NPLCC Science Coordinator with this information in the Project Metadata. Where applicable, a sample or physical collection preservation plan will be defined in the project’s DMP.

Ongoing Data Management: Upon transfer of data from a PI to the NPLCC, the NPLCC will become responsible for providing the long-term maintenance and public access to this data.

Project Close-Out

When all requirements have been fulfilled for a given project, the NPLCC Science Coordinator will notify the project PI, the S-TEK subcommittee and the Steering Committee that the project is completed.  Completion will be recorded in the Project Management Database, and all deliverables and data sets will be archived in appropriate systems.  Project outcomes, except for exceptions noted above in this guidance, will be made publically available, and the NPLCC will utilize these outcomes in targeted communications with NPLCC partners, natural resource practitioners, and the public.

If deemed appropriate, the NPLCC will invest a small amount of additional funds to convene the project PIs, the Steering Committee, and additional management entities to ensure that the information is understood and provided in a format/scale that can be used by managers. Study results would be presented and their implications explored.

Appendices

Appendix I:  Project Pre-Proposal Template

Appendix II:  Project Proposal Template

Appendix III:  Conflict of Interest and Confidentiality Agreement

Appendix IV:  Project Management Database (Under development)

Appendix V: Progress Report Template (Under development)

Appendix VI:  Data Management Plan Template

Appendix VII:  Deliverable Review Template (Under development)