## Sheet1
NPLCC Project Status - Completed Projects and Examples Ongoing Projects
Priority Topic | Title | Lead PI | Organization | Project Status | Start Date | End Date | NPLCC Funding | Workshops | List Deliverables and Dates | Communication & Outreach | Products received/completed
B | Mapping Pacific Northwest Riparian Areas: Measuring Current Condition And Prioritizing For Climate Change Adaptation | Meade Crosby | University of Washington | Completed | 2012-09-01 | 2013-12-31 | 20000 |  |  | Webinar Scheduled | Final Report submitted
B, Pre-strategy | North Pacific Forest Landscape Corridor and Connectivity Project: Assessing Landscape and Species Vulnerability | Erin Landguth | University of Montana | Completed | 2011-09-15 | 2012-12-30 | 41243 |  |  |  | Final Report posted, http://npflcc.dbs.umt.edu/
B; Pre-strategy | Current and Future Distribution and Abundance of North Pacific Birds in the Context of Climate Change | Grant Ballard | PRBO Conservation Science | Completed | 2011-09-15 | 2012-12-30 | 95000 |  |  | Webinar Posted | Final Report posted, http://www.avianknowledgenorthwest.net/distributionmodels, http://data.prbo.org/apps/nplcc/
B; Pre-strategy | The Washington Connected Landscapes Project: Providing Analysis Tools for Regional Connectivity and Climate Adaptation Planning | Brad McRae | The Nature Conservancy | Completed | 2011-09-15 | 2013-12-31 | 76000 |  |  | Webinar Scheduled | Final Report posted
B; Pre-strategy | Creating a Soil Vulnerability Index to Identify Drought Sensitive Areas | Dominique Bachelet | Conservation Biology Institute | Completed | 2011-09-15 | 2013-12-31 | 99500 |  |  | Webinar Posted | Interim Report received
C; Pre-strategy | Humboldt Nay NWR Sea-level rise modeling | John Takekawa | USGS, Western Ecological Research Center | Completed | 2011-08-25 | 2013-09-30 | 28000 |  | Builds on work funded by CA LCC |  | Final Report posted, raw data currently resides with USGS
Pre-strategy, doesn't fit categories well | A Conservation Priorities Tool for the NPLCC | Michael Mertens | Ecotrust | Completed | 2011-09-15 | 2012-12-30 | 95000 |  |  |  | Final Report posted
Pre-strategy, doesn't fit categories well | Modeling Climate Change Effects on the Hydrology of Pacific Northwest Wetland Ecosystems | Alan Hamlet | University of Washington | Completed | 2011-09-15 | 2013-03-31 | 99424 |  |  | Webinar Posted | Final Report posted
Pre-strategy, doesn't fit categories well | Applying Vulnerability Assessment Tools to Plan for Climate Adaptation: Case Studies in the NPLCC | Josh Lawler | University of Washington | Completed | 2011-09-20 | 2014-03-31 | 72915 |  | Builds on work funded by GNLCC |  | Final Report posted; Climate Adaptation Planning Guide for B.C. Provincial Parks posted; Report posted - Oregon Climate Adaptation Workshop
TEK | Correlation and climate sensitivity of human health and environmental indicators in the Salish Sea | Jamie Donatuto | Swinomish Indian Tribal Community | Completed | 2012-09-15 | 2013-12-31 | $49,000; co-funded NW CSC |  |  |  | Reports to be posted
C; Pre-strategy | Predicting the vulnerability of nearshore species and habitats to climate change effects | Deborah Reusser | USGS, Western Fisheries Research Center | In Progress | 2011-06-30 | 2013-12-31 | 95000 | Hosted Bivalve workshop in Newport, OR on Jan 13-15, 2014. Will host 8/26-28/2014 Workshop in Portland | Restricted website for expert data input 12/2011. Public Website 9/2012. Final Report to USFWS including peer review pubs over the life of the project 1/2013. | Highlighted in Western Fisheries Research Center Newsletter-workshop on bivalves for this project | Draft report received. Workshop on bivalve experts completed Jan. 2014. Workshop scheduled for Aug 2014 of trait based framework.
TEK | Implementing ecosystem-based management in the central coast of British Columbia: Support for Heiltsuk participation in the strategic landscape reserve design process | Laurie Whitehead | Heiltsuk Integrated Resource Management Department | In Progress | 2012-01-01 | 2014-06-30 | 50000 |  | Create and field verify map polygons- traditional First Nation forest and heritage resources, old growth forest, aquatic and biodiversity values in Land Use Objectives estabished in Ministerial Order; 10 Focus groups, community information and input sessions |  | Interim Report received
A | Developing a comprehensive interagency stream temperature database and high-resolution NorWeST climate scenarios for the NPLCC | Dan Isaak | USFS | In Progress | 2013-08-06 | 2014-12-31 | 71700 | Assisting with EPA stream temperature workshop (Nov 2014); spatial statistics stream network workshop (May 15th) | Builds on work funded by GNLCC; 1)Comprehensive reigional temperature database, 2)spatially continuous maps and descriptive summaries of stream temperatures for historic and future climate conditions, 3) thermal habitat maps and descriptive summaries (e.g., total amount of habitat, temporal trends in habitat, fragmentation of habitat) for aquatic species of concern like eulachon and lamprey under historic and future climate conditions, and 4)spatially continuous maps showing the precision of temperature model outputs. 5)Presentations at conferences and workshops. 6)Peer-reviewed manuscripts. 7) Temperature database, maps, and model outputs will be posted to NorWeST website (http://www.fs.fed.us/rm/boise/AWAE/projects/NorWeST.html). | Posters
A | Using Beaver for Climate Change and Conservation Benefits | Mary Ann Bishop/ Janine Castro | Portland State University/ USFWS | In Progress | 2013-08-13 | 2015-09-30 | 43001 | Workshops scheduled - Fall 2014/ Winter 2015 | Comprehensive synthesis of science; workshops; synthesis report